## Project Plan
#NUM!
2.5
Project Plan for ISO 27001 |  |  |  | Pro tip ➜ use this as your main source of guidance during the certification project. We recommend to update your progress every week
STANDARD |  | ISO 27001 |  |  | YOU'RE ON WEEK | 117
PROJECT OWNERS
COMPANY NAME |  |  |  |  | WEEKS UNTIL DEADLINE
PROJECT START DATE |  | 2024-05-23
EXPECTED DATE OF CERTIFICATION |  | 2024-07-31 |  |  | PROJECT PROGRESSION | 0%
↓ Hover your mouse through the headers below to understand the meaning of each one of them ↓
Phase |  | Prefix | Tasks | Details |  | Progress (per task) | Progress (phase) | Comments
1 | Project setup kick-off | 1.1 | Kick-off meeting with your team and Secfix | In the kickoff meeting, your CSM will share essential information about the ISO27001 process, explain the project plan and introduce you to the tools you will use. |  | 0% | 0%
|  | 1.2 | Get auditor introduction | Learn more about the role of the auditor here. |  | 0%
|  | 1.3 | Schedule stage 1 and 2 audits and sign the certification quote | Get an overwiev about the audit stages here and how much an ISO 27001 certification costs here. |  | 0%
0%
2 | Implementation phase | 2.1 | Complete asset inventory | Get more info about how to work on asset inventory here. |  | 0% | 0%
|  | 2.2 | Complete the security awareness training | Learn more about security awareness training here. |  | 0%
|  | 2.3 | Complete device security monitoring | You can use a monitoring device like an MDM or the Secfix agent to complete this task. Read more about it here. |  | 0%
|  | 2.4 | Read and write policies | Learn more about how to work on policies here |  | 0%
|  | 2.5 | Employees to read/accept policies | Learn more about how to read/accept policies here. |  | 0%
|  | 2.6 | Complete Risk Assessment | Learn more about how to conduct a risk assessment here. |  | 0%
|  | 2.7 | Complete Vendor Management | Learn more about how to work on vendor management here. |  | 0%
|  | 2.8 | Complete Access Management | Learn more about how to work on access management here. |  | 0%
3 | Audit readiness phase | 3.1 | Identify non-applicable controls in Statement of Applicability (SOA) | Learn more about non-applicable controls in SOA here! |  | 0% | 0%
|  | 3.2 | Write justifictions for exclusion on Statement of Applicability (SOA) | Learn more about justifications for exclusion in SOA here. |  | 0%
|  | 3.3 | Complete Management review | Learn more about how to work on a management review here. |  | 0%
|  | 3.4 | Conduct an internal audit | Learn more about how to conduct internal audits here. |  | 0%
4 | Audit phase | 4.1 | Complete stage 1 audit | Read more about the stages of ISO 27001 here. |  | 0% | 0%
|  | 4.2 | Remediate findings of stage 1 audit |  |  | 0%
|  | 4.3 | Complete stage 2 audit |  |  | 0%
|  | 4.4 | Remediate findings of stage 2 audit |  |  | 0%
|  | 4.5 | Obtain certification + audit report |  |  | 0%
5 | Maintenance phase | 5.1 | Add audit findings to Corrective Action Plan | Learn more about how to create a corrective action plan here. |  | 0% | 0%
|  | 5.2 | Assign tasks to audit findings | Learn more about how to create and assign tasks for audit findings here. |  | 0%
|  | 5.3 | Assign owners to finding tasks |  |  | 0%
|  | 5.4 | Assign deadlines to audit findings | Learn more about how to assign deadlines to audit findings here. |  | 0%
|  | 5.5 | Have an internal meeting to discuss the execution of maintenance | Learn more about how to conduct regular meetings to maintain your ISMS here. |  | 0%